PRODUCT REQUIREMENTS DOCUMENT

AI-Accelerated Design of Next-Generation
Chemogenetic Actuators

BIOEHSC 2026 Competition Project

UC Berkeley  •  April 4, 2026

Document Version: 1.0

Date: February 25, 2026

Status: Active Development — Week 3 of 7

# REVISION HISTORY

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Feb 25, 2026 | Project Lead | Initial PRD creation from Master Document |
| 1.1 | TBD | — | Post-Module 1 completion updates |
| 1.2 | TBD | — | Post-Module 2 completion updates |
| 2.0 | TBD | — | Final pre-competition release |

# TABLE OF CONTENTS

1.  Executive Summary

2.  Project Scope & Objectives

3.  System Architecture Overview

4.  Module 1 Spec: Structure Prediction (AlphaFold 3)

5.  Module 2 Spec: Actuator Evaluation Engine (RDKit + SwissADME)

6.  Module 3 Spec: Streamlit Integration Dashboard

7.  Data Specifications & Schemas

8.  User Interface & Experience Specification

9.  Testing & Validation Strategy

10.  Deployment & Infrastructure

11.  Week-by-Week Execution Plan

12.  Risk Register & Mitigations

13.  Acceptance Criteria & Definition of Done

14.  Dependencies & External Services

15.  Appendix: File Structure & Naming Conventions

# 1. EXECUTIVE SUMMARY

## 1.1 Product Vision

This PRD defines the complete technical specification for building a three-module AI-powered computational pipeline that compresses the chemogenetic actuator design cycle from years to days. The pipeline integrates protein structure prediction, computational drug screening, and an interactive analysis dashboard into a single researcher-facing tool.

## 1.2 Problem Statement

Chemogenetic actuator drugs (the compounds that activate DREADDs) suffer from critical flaws: off-target activity, uncontrolled BBB permeability, and limited selectivity. Designing better actuators currently requires 5–7 years of experimental work including cryo-EM structure determination, million-compound library screening, and extensive animal testing. The most recent chemogenetic system (HCAD, Cell 2024) took seven years from conception to publication.

## 1.3 Solution Summary

A computational pipeline consisting of three integrated modules, built entirely with free and open-source tools, capable of running on a standard laptop with internet access:

- Module 1 — Structure Prediction: AlphaFold 3 Server for rapid DREADD 3D structure prediction, validated against published cryo-EM experimental structures via RMSD analysis.

- Module 2 — Actuator Evaluation: RDKit + SwissADME for automated molecular property calculation, BBB permeability prediction, Lipinski compliance, and drug-likeness scoring across 6 known DREADD actuators.

- Module 3 — Integration Dashboard: A Streamlit web application chaining Modules 1 and 2 into a unified interface with 3D structure viewing, compound comparison, new-compound evaluation, and pipeline visualization.

## 1.4 Key Metrics & Success Criteria

| Metric | Target | Measurement Method |
| --- | --- | --- |
| AlphaFold backbone RMSD vs cryo-EM | < 3.0 Å for hM4Di & hM3Dq | BioPython Superimposer against PDB 7WC6/7WC7 |
| Binding pocket RMSD | < 5.0 Å for key residues | Subset RMSD on binding pocket atoms |
| Actuator property accuracy | RDKit values within 5% of PubChem reference | Cross-validation against PubChem + SwissADME |
| BBB prediction concordance | Correct classification for all 6 compounds | Compare predictions vs. published experimental data |
| Dashboard load time | < 3 seconds on standard connection | Streamlit app benchmarking |
| Dashboard feature completeness | All 4 tabs functional with data | Manual QA against spec |
| Competition poster | 30×40 landscape, 8 key figures | Visual inspection against layout spec |
| Presentation timing | 12 min ±30 sec | Rehearsal timing |

## 1.5 Stakeholders

| Role | Responsibility | Decisions |
| --- | --- | --- |
| Project Lead (You) | All development, research, presentation | Architecture, scope, priorities |
| Competition Judges | Evaluation on Apr 4 | Scoring on rigor, innovation, presentation |
| Faculty Advisor (if any) | Guidance, feedback | Scope validation, scientific review |

# 2. PROJECT SCOPE & OBJECTIVES

## 2.1 Specific Aims

Aim 1: Validate AlphaFold 3 for DREADD Structure Prediction Compare AF3-predicted structures of hM4Di and hM3Dq against experimental cryo-EM structures (PDB: 7WC6, 7WC7, 7WC8). Quantify accuracy via backbone RMSD and binding pocket RMSD. Analyze per-residue confidence (pLDDT) with focus on binding pocket residues.

Aim 2: Build Computational Actuator Evaluation Platform Characterize 6 known DREADD actuators: CNO, clozapine, DCZ, Compound 21, olanzapine, perlapine. Calculate molecular descriptors (MW, LogP, TPSA, HBD, HBA, rotatable bonds, aromatic rings, Fsp3). Predict BBB permeability using rule-based thresholds and SwissADME BOILED-Egg model. Score Lipinski Rule of Five compliance and overall drug-likeness.

Aim 3: Integrate into Functional Streamlit Prototype Build 4-tab dashboard: Structure Viewer, Actuator Comparison, New Compound Evaluator, Pipeline Overview. Demonstrate end-to-end workflow: sequence → structure → drug evaluation → ranking. Deploy locally for live demo at competition.

## 2.2 In-Scope

- AlphaFold 3 Server predictions for wild-type M3/M4, mutant hM3Dq/hM4Di, and protein-ligand complexes (7 total jobs)

- RMSD calculations (backbone + binding pocket) using BioPython

- pLDDT confidence analysis and per-residue confidence visualization

- RDKit molecular property calculation for 6 actuator compounds

- BBB permeability prediction via rule-based thresholds (MW < 450, LogP 1–3, TPSA < 90, HBD ≤ 3)

- SwissADME BOILED-Egg screenshots for cross-validation

- Streamlit 4-tab dashboard with py3Dmol 3D viewer, plotly charts, pandas tables

- 30×40 research poster, 12-min presentation, 2-min pitch, midpoint video

## 2.3 Out of Scope (Explicit Exclusions)

- Novel actuator drug design or generation (this is a screening/evaluation tool, not generative)

- Molecular docking simulations (AutoDock, Glide, etc.)

- Molecular dynamics simulations (GROMACS, AMBER, etc.)

- Wet lab experiments of any kind

- Animal model validation

- Full pharmacokinetic profiling beyond rule-based BBB prediction

- Cloud deployment of Streamlit app (local-only for competition demo; cloud is future work)

- Machine learning BBB prediction models (XGBoost, GNN — future work)

## 2.4 Future Work (Post-Competition)

- Generative AI module (deep RL) for de novo actuator candidate generation

- Molecular docking integration (AutoDock Vina) for binding affinity prediction

- Cloud deployment on Streamlit Community Cloud or Heroku

- Experimental validation through university DREADD lab collaboration

- Expansion to non-DREADD chemogenetic systems (PSAMs, PAGERs, HCAD)

# 3. SYSTEM ARCHITECTURE OVERVIEW

## 3.1 High-Level Pipeline Flow

The system follows a linear three-module architecture where each module produces outputs consumed by downstream modules and/or the dashboard:

Pipeline Data Flow INPUT: DREADD amino acid sequence (UniProt + mutations applied manually) ↓ MODULE 1: AlphaFold 3 Server → .cif predicted structure + pLDDT/PAE confidence ↓ Validated against experimental .pdb files via RMSD MODULE 2: RDKit + SwissADME → Property table (MW, LogP, TPSA, HBD, HBA, BBB, Lipinski) ↓ Input: SMILES strings from PubChem MODULE 3: Streamlit Dashboard → Unified web interface rendering Modules 1 + 2 outputs ↓ OUTPUT: Interactive researcher tool with ranked actuator candidates

## 3.2 Module Dependency Map

| Module | Depends On | Produces | Consumed By |
| --- | --- | --- | --- |
| Module 1 (Structure) | AlphaFold Server, UniProt, PDB | .cif files, RMSD data, pLDDT arrays | Module 3 (dashboard display) |
| Module 2 (Actuator) | PubChem SMILES, RDKit, SwissADME | Property DataFrame, chemical space plots, BBB predictions | Module 3 (dashboard display) |
| Module 3 (Dashboard) | Modules 1 & 2 output files | Streamlit web app, poster figures, exported PNGs | Competition deliverables |

## 3.3 Technology Stack

| Layer | Technology | Version | Purpose |
| --- | --- | --- | --- |
| Language | Python | 3.10+ | All modules |
| Structure Prediction | AlphaFold 3 Server | Current (web) | DREADD 3D structure prediction |
| Structure Validation | BioPython | 1.83+ | PDB parsing, RMSD calculation |
| Structure Visualization | py3Dmol + stmol | Latest | Interactive 3D molecular viewer |
| Cheminformatics | RDKit | 2024.03+ | Molecular property calculation |
| Pharmacokinetics | SwissADME | Web service | BOILED-Egg BBB model, ADME properties |
| Dashboard Framework | Streamlit | 1.30+ | Web application framework |
| Data Handling | pandas | 2.0+ | DataFrames, CSV I/O |
| Static Visualization | matplotlib | 3.8+ | Publication-quality figures |
| Interactive Visualization | plotly | 5.18+ | Dashboard charts |
| Numerical Computing | numpy | 1.26+ | Array operations, RMSD math |

## 3.4 Hardware Requirements

All components run on a standard laptop with internet access. No GPU, HPC cluster, or cloud compute is required.

| Component | Requirement | Notes |
| --- | --- | --- |
| CPU | Any modern x86/ARM | RDKit calculations are sub-second for 6 compounds |
| RAM | 4 GB minimum | BioPython PDB parsing is lightweight |
| Storage | < 500 MB total | PDB files ~5 MB each, .cif files ~2 MB each |
| Internet | Required for Modules 1 + 2 (web services) | AlphaFold Server, SwissADME, PubChem |
| Browser | Any modern browser | AlphaFold Server, SwissADME web interface |
| OS | Windows, macOS, or Linux | Python + RDKit available on all platforms |

# 4. MODULE 1 SPEC: STRUCTURE PREDICTION (AlphaFold 3)

## 4.1 Purpose

Predict 3D structures of DREADD receptors (hM4Di, hM3Dq) from amino acid sequences using AlphaFold 3, then validate predictions against published cryo-EM experimental structures by computing RMSD.

## 4.2 Input Specifications

### 4.2.1 Protein Sequences

| Receptor | UniProt ID | Gene | Length | DREADD Mutations |
| --- | --- | --- | --- | --- |
| Human M4 (wild-type) | P08173 | CHRM4 | 479 aa | None |
| hM4Di (DREADD) | P08173 + mutations | CHRM4 | 479 aa | Y113C, A203G |
| Human M3 (wild-type) | P20309 | CHRM3 | 590 aa | None |
| hM3Dq (DREADD) | P20309 + mutations | CHRM3 | 590 aa | Y149C, A239G |

### 4.2.2 Ligand Inputs (for complex predictions)

| Ligand | PubChem CID | SMILES Source | Used With |
| --- | --- | --- | --- |
| DCZ (deschloroclozapine) | 44601286 | PubChem | hM4Di (Job 5), hM3Dq (Job 6) |
| CNO (clozapine-N-oxide) | 135398508 | PubChem | hM3Dq (Job 7) |

### 4.2.3 Experimental Reference Structures

| PDB Code | Complex | Ligand | Resolution | Validation Target |
| --- | --- | --- | --- | --- |
| 7WC6 | hM4Di–miniGo | DCZ | ~2.6 Å | AF3 hM4Di prediction |
| 7WC7 | hM3Dq–miniGq | DCZ | ~2.7 Å | AF3 hM3Dq prediction |
| 7WC8 | hM3Dq–miniGq | CNO | ~2.8 Å | DCZ vs CNO binding comparison |

## 4.3 AlphaFold Server Job Matrix

| Job # | Input | Ligand | Purpose | Priority |
| --- | --- | --- | --- | --- |
| 1 | Wild-type M4 (P08173) | None | GPCR baseline accuracy | P1 |
| 2 | Wild-type M3 (P20309) | None | GPCR baseline accuracy | P1 |
| 3 | hM4Di (Y113C + A203G) | None | Core DREADD prediction | P0 |
| 4 | hM3Dq (Y149C + A239G) | None | Core DREADD prediction | P0 |
| 5 | hM4Di + DCZ | DCZ CID:44601286 | Protein-ligand complex | P0 |
| 6 | hM3Dq + DCZ | DCZ CID:44601286 | Protein-ligand complex | P0 |
| 7 | hM3Dq + CNO | CNO CID:135398508 | Compare to PDB 7WC8 | P1 |

## 4.4 Processing Pipeline

### 4.4.1 Step-by-Step Workflow

- Retrieve wild-type sequences from UniProt (P08173 for M4, P20309 for M3)

- Apply DREADD mutations manually in a text editor (Y113C + A203G for hM4Di; Y149C + A239G for hM3Dq)

- Submit sequences to AlphaFold Server (alphafoldserver.com) — one job per prediction

- For protein-ligand jobs (5–7): add ligand via SMILES or CCD code in the AF3 interface

- Download output .cif files and confidence JSON for each prediction

- Download experimental .pdb files from RCSB PDB (7WC6, 7WC7, 7WC8)

- Convert .cif to .pdb if needed using BioPython or Open Babel for RMSD compatibility

- Run RMSD calculation script (backbone CA atoms + binding pocket subset)

- Extract pLDDT scores per residue from AF3 output; generate confidence plot

- Save all outputs to project data directory for Module 3 consumption

### 4.4.2 RMSD Calculation Specification

Two RMSD metrics are computed for each prediction:

| Metric | Atoms Used | Expected Range | Interpretation |
| --- | --- | --- | --- |
| Backbone RMSD | All Cα atoms in receptor chain | 1.5–3.0 Å | Overall fold accuracy; < 2 Å = excellent, < 3 Å = good |
| Binding Pocket RMSD | Cα + side-chain heavy atoms at positions 3.33, 5.46 and surrounding residues | 3.0–5.0 Å | Drug binding site accuracy; critical for actuator screening relevance |

### 4.4.3 Binding Pocket Residue Definitions

These residue sets define the subset of atoms used for binding pocket RMSD:

hM3Dq binding pocket (from Shao et al., Nature 2022): C149 (3.33), G239 (5.46), D148, S152, T235, F222, W525, Y529, N507

hM4Di binding pocket: C113 (3.33), G203 (5.46), plus corresponding residues from structural alignment

## 4.5 Output Specifications

| Output | Format | Location | Used By |
| --- | --- | --- | --- |
| Predicted structures | .cif (mmCIF) | data/structures/predicted/ | Module 3 (3D viewer) |
| Experimental structures | .pdb | data/structures/experimental/ | Module 3 (3D viewer), RMSD script |
| RMSD results | rmsd_results.csv | data/results/ | Module 3 (table + bar chart) |
| pLDDT scores | plddt_scores.json per structure | data/results/ | Module 3 (confidence plot) |
| Structure overlay renders | .png (PyMOL/ChimeraX) | figures/ | Poster, presentation |

## 4.6 Acceptance Criteria for Module 1

- All 7 AF3 jobs submitted and completed with output .cif files downloaded

- All 3 experimental PDB files (7WC6, 7WC7, 7WC8) downloaded and parseable by BioPython

- Backbone RMSD computed for at least hM4Di and hM3Dq against corresponding PDB structures

- Binding pocket RMSD computed for at least hM4Di and hM3Dq

- pLDDT scores extracted and plotted for at least 2 predicted structures

- All outputs saved in correct directory structure for Module 3 consumption

- At least one structural overlay figure generated (predicted vs. experimental) for poster

# 5. MODULE 2 SPEC: ACTUATOR EVALUATION ENGINE

## 5.1 Purpose

Evaluate 6 known DREADD actuator compounds across molecular properties, BBB permeability, Lipinski compliance, and drug-likeness to create a ranked comparison enabling researchers to select optimal actuators.

## 5.2 Input Specifications

### 5.2.1 Target Compounds

| Compound | PubChem CID | Role in Project | Known Issues |
| --- | --- | --- | --- |
| CNO (clozapine-N-oxide) | 135398508 | Original actuator (problematic baseline) | Converts to clozapine in vivo |
| Clozapine | 2818 | Off-target metabolite of CNO | Binds D2, 5-HT2A, H1, muscarinic |
| DCZ (deschloroclozapine) | 44601286 | Current preferred actuator | Crosses BBB indiscriminately |
| Compound 21 (C21) | 135445020 | Alternative actuator | Lower potency, some off-target |
| Olanzapine | 4585 | Repurposed antipsychotic | Significant off-target effects |
| Perlapine | 4748 | Sedative with DREADD activity | Limited characterization |

### 5.2.2 Input Data Format

Each compound is defined by its SMILES string, retrieved from PubChem programmatically or manually:

- Primary input: compounds.csv with columns [name, pubchem_cid, smiles]

- SMILES retrieval: PubChem PUG REST API or manual copy from PubChem compound page

- Fallback: hardcoded SMILES dictionary in the evaluation script

## 5.3 Property Calculation Specification

### 5.3.1 RDKit Molecular Descriptors

| Property | RDKit Function | Unit | BBB Threshold | Lipinski Threshold |
| --- | --- | --- | --- | --- |
| Molecular Weight (MW) | Descriptors.MolWt() | Da | < 450 | < 500 |
| LogP (lipophilicity) | Descriptors.MolLogP() | unitless | 1–3 | < 5 |
| TPSA | Descriptors.TPSA() | Å² | < 90 | N/A |
| H-bond Donors (HBD) | Descriptors.NumHDonors() | count | ≤ 3 | ≤ 5 |
| H-bond Acceptors (HBA) | Descriptors.NumHAcceptors() | count | N/A | ≤ 10 |
| Rotatable Bonds | Descriptors.NumRotatableBonds() | count | N/A | N/A |
| Aromatic Rings | Descriptors.NumAromaticRings() | count | N/A | N/A |
| Fraction Csp3 | Descriptors.FractionCSP3() | 0–1 | N/A | N/A |

### 5.3.2 BBB Permeability Prediction Rules

A compound is classified as BBB-penetrant only if ALL four criteria are met:

- MW < 450 Da

- LogP between 1.0 and 3.0 (inclusive)

- TPSA < 90 Å²

- HBD ≤ 3

If any single criterion fails, the compound is classified as "Non-penetrant". This is a conservative rule-based approach; ML models would be more nuanced but are out of scope.

### 5.3.3 Lipinski Rule of Five Scoring

Count violations of: MW ≥ 500, LogP ≥ 5, HBD > 5, HBA > 10. Compounds with 0–1 violations are considered drug-like. Compounds with 2+ violations are flagged.

## 5.4 SwissADME Cross-Validation

For each compound, run SwissADME (swissadme.ch) with the SMILES string to obtain:

- BOILED-Egg plot position (white = GI absorption, yellow = BBB penetrant)

- Physicochemical property profile for cross-validation against RDKit values

- P-gp substrate prediction (drug efflux transporter)

- Synthetic accessibility score

Screenshot the BOILED-Egg plot for the poster. Export properties to validate RDKit calculations match within 5%.

## 5.5 Visualization Specifications

| Figure | Type | X-Axis | Y-Axis | Additional Elements |
| --- | --- | --- | --- | --- |
| Chemical Space Plot | Scatter | LogP | TPSA (Å²) | BBB threshold lines (TPSA=90, LogP=1/3), green shading for penetrant zone, bubble size = MW, color = BBB status |
| Property Radar Chart | Radar/Spider | Properties (MW, LogP, TPSA, HBD, HBA, RotBonds) | Normalized 0–1 scale | One trace per compound, overlay for comparison |
| Compound Comparison Table | Sortable table | N/A | N/A | Color-coded cells: green=pass, red=fail for BBB criteria |
| Lipinski Compliance Bar | Stacked bar | Compound name | Violation count (0–4) | Color segments for each rule |

## 5.6 Output Specifications

| Output | Format | Location | Used By |
| --- | --- | --- | --- |
| Property table | actuator_properties.csv | data/results/ | Module 3, poster |
| Chemical space plot | chemical_space.png (300 DPI) | figures/ | Poster, presentation, Module 3 |
| Radar charts | radar_chart.png per compound | figures/ | Module 3, poster |
| BOILED-Egg screenshots | boiled_egg.png | figures/ | Poster |
| Evaluation script | evaluate_actuators.py | src/module2/ | Module 3 imports |

## 5.7 Acceptance Criteria for Module 2

- All 6 compounds successfully parsed from SMILES (RDKit MolFromSmiles returns valid molecule)

- All 8 molecular descriptors calculated for each compound

- BBB classification matches known experimental behavior for DCZ (penetrant) and CNO (non-penetrant metabolized to clozapine)

- RDKit values within 5% of PubChem reference values for MW and LogP

- Chemical space plot generated with all 6 compounds labeled and BBB zones visible

- SwissADME BOILED-Egg screenshots captured for at least DCZ, CNO, and clozapine

- All outputs saved in correct format/location for Module 3 consumption

# 6. MODULE 3 SPEC: STREAMLIT INTEGRATION DASHBOARD

## 6.1 Purpose

Provide a unified, interactive web interface that chains Modules 1 and 2 into a single researcher-facing tool. The dashboard serves dual purposes: (1) as a functional prototype demonstrating the pipeline concept, and (2) as a live demo during the competition presentation.

## 6.2 Application Structure

| Component | Implementation | Description |
| --- | --- | --- |
| Entry point | app.py | Main Streamlit application with sidebar navigation |
| Tab 1: Structure Viewer | tabs/structure_viewer.py | 3D molecular viewer (py3Dmol), RMSD table, pLDDT confidence plot |
| Tab 2: Actuator Comparison | tabs/actuator_comparison.py | Property table, radar chart, chemical space plot |
| Tab 3: Evaluate New Compound | tabs/new_compound.py | SMILES input box, instant property calc, comparison overlay |
| Tab 4: Pipeline Overview | tabs/pipeline_overview.py | Flow diagram, methodology text, links to tools |
| Shared utilities | utils/ | Data loading, property calculation, plotting functions |

## 6.3 Tab-by-Tab Feature Specification

### 6.3.1 Tab 1: Structure Viewer

| Feature | Implementation | Priority | Details |
| --- | --- | --- | --- |
| DREADD selector | st.selectbox | P0 | Dropdown: hM4Di, hM3Dq, wild-type M4, wild-type M3 |
| 3D structure viewer | py3Dmol + stmol | P0 | Render selected predicted structure; cartoon + spectrum coloring |
| Overlay toggle | st.checkbox | P0 | Overlay predicted vs. experimental structure in same viewer |
| Style controls | st.radio | P1 | Cartoon / Surface / Ball-and-Stick / Binding pocket highlight |
| RMSD results table | st.dataframe | P0 | Show backbone RMSD + pocket RMSD for each structure pair |
| RMSD bar chart | plotly bar | P0 | Grouped bar chart: backbone vs pocket RMSD per structure |
| pLDDT confidence plot | plotly line | P0 | Per-residue pLDDT with color bands (>90 green, 70-90 yellow, <70 red) |
| Binding pocket residue highlight | py3Dmol selection | P1 | Highlight key binding pocket residues in 3D viewer (C113/C149, G203/G239) |

### 6.3.2 Tab 2: Actuator Comparison

| Feature | Implementation | Priority | Details |
| --- | --- | --- | --- |
| Property summary table | st.dataframe (styled) | P0 | All 6 compounds × all properties; color-coded pass/fail cells |
| Compound multi-select | st.multiselect | P0 | Select 2+ compounds for head-to-head comparison |
| Chemical space scatter | plotly scatter | P0 | LogP vs TPSA with BBB zones, bubble size = MW |
| Radar/spider chart | plotly radar | P1 | Normalized properties overlay for selected compounds |
| BBB prediction summary | st.metric cards | P0 | Green check / red X for each BBB criterion per compound |
| Lipinski violations bar | plotly bar | P1 | Stacked bar showing violation count per compound |
| Export to CSV | st.download_button | P2 | Download property table as CSV |

### 6.3.3 Tab 3: Evaluate New Compound

| Feature | Implementation | Priority | Details |
| --- | --- | --- | --- |
| SMILES text input | st.text_input | P0 | User pastes SMILES; instant validation via RDKit |
| Instant property calculation | RDKit on input | P0 | Display all 8 properties + BBB + Lipinski immediately on input |
| 2D structure image | rdkit.Chem.Draw | P0 | Render 2D molecular structure from SMILES |
| Comparison overlay | plotly scatter | P0 | Add new compound to existing chemical space plot |
| Similarity to known actuators | RDKit fingerprints | P2 | Tanimoto similarity score to each known actuator |
| Property card | st.columns + st.metric | P0 | Visual card showing MW, LogP, TPSA, BBB status with delta vs. DCZ |

### 6.3.4 Tab 4: Pipeline Overview

| Feature | Implementation | Priority | Details |
| --- | --- | --- | --- |
| Pipeline flow diagram | Embedded image or Mermaid | P0 | Visual showing Input → Module 1 → Module 2 → Dashboard → Output |
| Module descriptions | st.markdown sections | P0 | Brief description of each module's role and tools |
| Tool links | st.markdown with URLs | P1 | Clickable links to AlphaFold Server, SwissADME, PubChem, RCSB PDB |
| Performance stats | st.metrics | P1 | "5 min per structure prediction", "< 1 sec per compound evaluation" |
| Cost comparison table | st.dataframe | P1 | Traditional vs. AI pipeline cost and time comparison |

## 6.4 UI/UX Specifications

| Element | Specification |
| --- | --- |
| Page title | "AI-Accelerated Chemogenetic Actuator Design" |
| Sidebar width | Default Streamlit sidebar |
| Color scheme | Streamlit default light theme; accent blue #2E75B6 for headers |
| py3Dmol viewer size | Width: 700px, Height: 500px |
| Chart dimensions | Width: 100% container, Height: 400–500px |
| Table max rows visible | 6 (all compounds visible without scroll) |
| Font | Streamlit default (Source Sans Pro) |
| Loading states | st.spinner for any computation > 0.5 seconds |
| Error handling | st.error for invalid SMILES, st.warning for missing data files |

## 6.5 Acceptance Criteria for Module 3

- Streamlit app launches without errors via 'streamlit run app.py'

- All 4 tabs navigate correctly from sidebar

- Tab 1: At least 2 structures render in 3D viewer; RMSD table and bar chart display correctly

- Tab 2: All 6 compounds displayed in property table and chemical space plot

- Tab 3: Valid SMILES input produces instant property card and chemical space overlay

- Tab 3: Invalid SMILES input produces clear error message (not a crash)

- Tab 4: Pipeline diagram and module descriptions render

- App loads in < 3 seconds on localhost

- All charts are interactive (hover tooltips, zoom) via plotly

# 7. DATA SPECIFICATIONS & SCHEMAS

## 7.1 File Directory Structure

Project Root: chemogenetic-pipeline/ ├── app.py # Streamlit entry point ├── requirements.txt # Python dependencies ├── README.md # Project documentation ├── src/ │ ├── module1/ │ │ ├── rmsd_calculator.py # BioPython RMSD computation │ │ └── plddt_parser.py # AF3 confidence score extraction │ ├── module2/ │ │ ├── evaluate_actuators.py # RDKit property calculation engine │ │ └── compounds.py # SMILES dictionary + compound metadata │ └── utils/ │ ├── data_loader.py # CSV/PDB/CIF file loading │ └── plotting.py # Shared visualization functions ├── tabs/ │ ├── structure_viewer.py │ ├── actuator_comparison.py │ ├── new_compound.py │ └── pipeline_overview.py ├── data/ │ ├── structures/ │ │ ├── predicted/ # AF3 .cif output files │ │ └── experimental/ # PDB .pdb files (7WC6, 7WC7, 7WC8) │ ├── compounds/ │ │ └── compounds.csv # Name, CID, SMILES for all 6 actuators │ └── results/ │ ├── rmsd_results.csv │ ├── actuator_properties.csv │ └── plddt_scores/ # JSON files per prediction └── figures/ # All exported plots and renders

## 7.2 CSV Schema Definitions

### 7.2.1 compounds.csv

| Column | Type | Example | Notes |
| --- | --- | --- | --- |
| name | string | DCZ | Human-readable compound name |
| pubchem_cid | integer | 44601286 | PubChem Compound ID |
| smiles | string | C1=CC=C2C(=C1)... | Canonical SMILES from PubChem |
| role | string | preferred_actuator | One of: baseline, metabolite, preferred, alternative, repurposed, experimental |

### 7.2.2 rmsd_results.csv

| Column | Type | Example | Notes |
| --- | --- | --- | --- |
| prediction_name | string | hM4Di_apo | Descriptive name for the AF3 prediction |
| experimental_pdb | string | 7WC6 | PDB code used as reference |
| backbone_rmsd_angstrom | float | 2.34 | Backbone Cα RMSD in Å |
| pocket_rmsd_angstrom | float | 4.12 | Binding pocket RMSD in Å |
| n_atoms_backbone | integer | 350 | Number of Cα atoms used |
| n_atoms_pocket | integer | 18 | Number of pocket atoms used |
| af3_version | string | 3.0 | AlphaFold version used |

### 7.2.3 actuator_properties.csv

| Column | Type | Example | Notes |
| --- | --- | --- | --- |
| name | string | DCZ | Compound name |
| mw | float | 312.3 | Molecular weight in Da |
| logp | float | 2.85 | Crippen LogP |
| tpsa | float | 43.2 | Topological Polar Surface Area in Å² |
| hbd | integer | 1 | H-bond donors |
| hba | integer | 3 | H-bond acceptors |
| rotatable_bonds | integer | 1 | Rotatable bond count |
| aromatic_rings | integer | 3 | Aromatic ring count |
| fsp3 | float | 0.15 | Fraction Csp3 (0–1) |
| bbb_predicted | string | Penetrant | Penetrant or Non-penetrant |
| lipinski_violations | integer | 0 | Count of Lipinski violations (0–4) |

# 8. TESTING & VALIDATION STRATEGY

## 8.1 Module 1 Validation

| Test | Method | Pass Criteria | Status |
| --- | --- | --- | --- |
| AF3 job completion | All 7 jobs return .cif output | 7/7 jobs complete with no server errors | Pending |
| CIF file integrity | BioPython PDB parser loads without error | Parser returns structure object with atoms | Pending |
| PDB download integrity | BioPython parses 7WC6, 7WC7, 7WC8 | All 3 files load; chain A extractable | Pending |
| Backbone RMSD range | Calculated value vs literature | < 3.0 Å for hM4Di, hM3Dq | Pending |
| pLDDT extraction | Parse AF3 confidence output | pLDDT array length = sequence length | Pending |
| TM helix confidence | Mean pLDDT for TM regions | > 80 for all transmembrane helices | Pending |

## 8.2 Module 2 Validation

| Test | Method | Pass Criteria | Status |
| --- | --- | --- | --- |
| SMILES parsing | RDKit MolFromSmiles for all 6 | No None returns; all valid molecules | Pending |
| MW accuracy | Compare RDKit MW to PubChem value | Within 0.5 Da for all compounds | Pending |
| LogP accuracy | Compare RDKit to SwissADME value | Within 0.5 units for all compounds | Pending |
| BBB classification: DCZ | Rule-based prediction | Classified as Penetrant | Pending |
| BBB classification: CNO | Rule-based prediction | Consistent with known metabolism issue | Pending |
| Lipinski: no false positives | Violation count for known drug-like compounds | DCZ and clozapine have 0 violations | Pending |
| Plot generation | Chemical space plot + radar | PNG exported at 300 DPI, all compounds labeled | Pending |

## 8.3 Module 3 Validation

| Test | Method | Pass Criteria | Status |
| --- | --- | --- | --- |
| App launch | streamlit run app.py | No errors; page renders in browser | Pending |
| Tab navigation | Click all 4 tabs | Each tab loads without error | Pending |
| 3D viewer rendering | Load hM4Di structure | Structure visible; rotation/zoom work | Pending |
| SMILES input: valid | Enter DCZ SMILES | Properties display; chemical space updates | Pending |
| SMILES input: invalid | Enter 'not_a_smiles' | st.error message; no crash | Pending |
| Performance | Page load time | < 3 seconds on localhost | Pending |
| Data freshness | All CSVs load correctly | No stale or missing data errors | Pending |

# 9. DEPLOYMENT & INFRASTRUCTURE

## 9.1 Competition Day Setup (Local)

- Ensure laptop has Python 3.10+, all dependencies installed (pip install -r requirements.txt)

- Verify all data files present in data/ directory

- Test: run 'streamlit run app.py' and check all 4 tabs

- Pre-load structures in browser tabs as backup (PyMOL/ChimeraX renders)

- Bring portable Wi-Fi hotspot (backup for AlphaFold Server demo if needed)

- Have poster printed at 30×40 inches, landscape orientation

- Load presentation on laptop + USB backup

## 9.2 Environment Setup Script

setup.sh (one-time environment creation) #!/bin/bash conda create -n chemogenetic python=3.10 -y conda activate chemogenetic conda install -c conda-forge rdkit -y pip install streamlit biopython py3Dmol stmol pandas matplotlib plotly numpy echo 'Environment ready. Run: streamlit run app.py'

## 9.3 requirements.txt

requirements.txt streamlit>=1.30.0 biopython>=1.83 py3Dmol>=2.0.0 stmol>=0.0.9 pandas>=2.0.0 matplotlib>=3.8.0 plotly>=5.18.0 numpy>=1.26.0 rdkit # Install via conda: conda install -c conda-forge rdkit

## 9.4 Future: Cloud Deployment (Post-Competition)

| Platform | Pros | Cons | Cost |
| --- | --- | --- | --- |
| Streamlit Community Cloud | Free, native Streamlit support, GitHub integration | RDKit may need custom setup, cold starts | Free |
| Heroku | Easy deploy, good Python support | RDKit buildpack needed, dyno sleep | Free tier limited |
| Render | Free tier, Docker support | Cold starts on free tier | Free |
| Railway | Simple deploy, good DX | Pricing per usage | $5/mo estimate |

# 10. WEEK-BY-WEEK EXECUTION PLAN

## Week 3: Feb 24 – Mar 2 — Module 1 (Structure Prediction)

| Day | Task | Deliverable | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| Mon | Download WT sequences from UniProt (P08173, P20309) | 2 FASTA files | P0 | 30 min |
| Mon | Apply DREADD mutations manually (Y113C/A203G, Y149C/A239G) | 2 mutant FASTA files | P0 | 30 min |
| Mon-Tue | Submit 7 AF3 jobs to AlphaFold Server | 7 job submissions | P0 | 2 hrs |
| Tue | Download experimental structures from PDB (7WC6, 7WC7, 7WC8) | 3 PDB files | P0 | 30 min |
| Wed | Collect AF3 results (.cif files + confidence data) | 7 .cif files + JSON | P0 | 1 hr |
| Wed-Thu | Write RMSD calculation script (BioPython) | rmsd_calculator.py | P0 | 3 hrs |
| Thu | Run RMSD calculations; populate rmsd_results.csv | rmsd_results.csv | P0 | 2 hrs |
| Fri | Extract pLDDT scores; create confidence plots | pLDDT line plots | P0 | 2 hrs |
| Sat-Sun | Generate structure overlay figures (PyMOL or ChimeraX) | overlay PNGs | P1 | 3 hrs |

## Week 4: Mar 3 – Mar 9 — Module 2 (Actuator Evaluation)

| Day | Task | Deliverable | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| Mon | Retrieve SMILES for all 6 compounds from PubChem | compounds.csv | P0 | 1 hr |
| Mon-Tue | Write evaluate_actuators.py (RDKit property engine) | evaluate_actuators.py | P0 | 4 hrs |
| Tue-Wed | Run evaluation; generate actuator_properties.csv | actuator_properties.csv | P0 | 1 hr |
| Wed | Run all 6 compounds through SwissADME; screenshot BOILED-Egg | 6 SwissADME screenshots | P0 | 2 hrs |
| Thu | Cross-validate RDKit vs SwissADME values; document discrepancies | Validation notes | P0 | 2 hrs |
| Thu-Fri | Create chemical space plot (LogP vs TPSA) | chemical_space.png | P0 | 2 hrs |
| Fri-Sat | Create radar charts and Lipinski compliance bar chart | Additional figures | P1 | 3 hrs |
| Sun | Review all Module 2 outputs; fix any issues | QA complete | P0 | 2 hrs |

## Week 5: Mar 10 – Mar 16 — Module 3 (Dashboard)

| Day | Task | Deliverable | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| Mon | Set up Streamlit project structure (app.py, tabs/, src/, data/) | Scaffold | P0 | 2 hrs |
| Mon-Tue | Build Tab 1: Structure Viewer (py3Dmol + RMSD table + pLDDT plot) | Tab 1 functional | P0 | 5 hrs |
| Wed | Build Tab 2: Actuator Comparison (table + chemical space + radar) | Tab 2 functional | P0 | 4 hrs |
| Thu | Build Tab 3: New Compound Evaluator (SMILES input + live calc) | Tab 3 functional | P0 | 4 hrs |
| Fri | Build Tab 4: Pipeline Overview (diagram + descriptions + stats) | Tab 4 functional | P0 | 3 hrs |
| Sat | Integration testing; error handling; loading states | All tabs stable | P0 | 4 hrs |
| Sun | Polish UI; add header/branding; final QA | Dashboard complete | P0 | 3 hrs |

## Week 6: Mar 17 – Mar 23 — Competition Materials

| Day | Task | Deliverable | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| Mon-Tue | Design and build 30×40 poster layout | Poster draft v1 | P0 | 6 hrs |
| Wed | Write 12-min academic presentation slides | Slide deck v1 | P0 | 4 hrs |
| Thu | Write 2-min industry pitch | Pitch script v1 | P0 | 2 hrs |
| Thu-Fri | Record midpoint video (60–120 sec) | Midpoint video | P0 | 3 hrs |
| Fri | Poster review and revisions | Poster draft v2 | P0 | 3 hrs |
| Sat-Sun | Presentation rehearsal (time to 12 min) | Timed run-through | P0 | 4 hrs |

## Week 7: Mar 24 – Apr 3 — Polish & Rehearse

| Day | Task | Deliverable | Priority | Est. Time |
| --- | --- | --- | --- | --- |
| Mon-Tue | Final poster revision; send to print | Poster final + print order | P0 | 3 hrs |
| Wed-Thu | Presentation polish; add transitions and backup slides | Slide deck final | P0 | 4 hrs |
| Fri | Full dress rehearsal with Q&A practice | Rehearsal complete | P0 | 3 hrs |
| Sat-Sun | Dashboard final QA; prepare laptop for demo day | System check complete | P0 | 2 hrs |
| Mon | Rest day / light review | — | P2 | — |
| Tue-Wed | Final rehearsal; pack materials | Competition ready | P0 | 2 hrs |
| Apr 4 (Fri) | COMPETITION DAY | Present at UC Berkeley | P0 | All day |

# 11. RISK REGISTER & MITIGATIONS

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | AlphaFold Server is down or rate-limited during Week 3 | Low | High | Submit all jobs Day 1; AlphaFold DB has pre-computed wild-type structures as backup |
| R2 | AF3 predictions have high RMSD (> 5 Å) | Medium | Medium | This IS a result — frame as honest assessment of AF3 limitations for DREADDs; compare to literature benchmarks |
| R3 | RDKit SMILES parsing fails for a compound | Low | Low | Use canonical SMILES from PubChem; fallback to InChI conversion |
| R4 | Streamlit py3Dmol rendering issues | Medium | Medium | Pre-render PyMOL/ChimeraX static images as fallback for poster and presentation |
| R5 | Competition day laptop failure | Low | Critical | USB backup of all files; cloud backup on Google Drive; printed screenshots of dashboard |
| R6 | Wi-Fi unavailable at competition venue | Medium | Low | Dashboard runs locally; all data files pre-downloaded; only SwissADME needs live internet |
| R7 | Time overrun on Module 1 delays Module 3 | Medium | High | Module 2 is independent of Module 1; can build in parallel. Dashboard can use mock data initially. |
| R8 | Poster printing delay | Low | High | Send to printer by end of Week 6 (1+ week buffer); identify backup print shop |
| R9 | pLDDT confidence is low for binding pocket | Medium | Medium | Frame as known AF3 limitation for flexible loop regions; cite literature on AF3 GPCR accuracy |
| R10 | Judge questions exceed preparation | Medium | Low | Q&A prep covers 12+ anticipated questions; "I don’t know but here’s how I’d find out" is acceptable |

# 12. ACCEPTANCE CRITERIA & DEFINITION OF DONE

## 12.1 Overall Project: Definition of Done

The project is considered complete when ALL of the following are true:

- Module 1: At least 4 of 7 AF3 predictions completed; RMSD calculated for hM4Di and hM3Dq; pLDDT plots generated

- Module 2: All 6 compounds evaluated; property table, chemical space plot, and BBB predictions generated

- Module 3: Streamlit app launches with all 4 tabs functional; live demo rehearsed

- Poster: 30×40 landscape poster printed with 8 key figures

- Presentation: 12-min slide deck timed and rehearsed; backup slides for Q&A

- Pitch: 2-min industry pitch scripted and timed

- Video: Midpoint video (60–120 sec) recorded and submitted

- GitHub: Repository with README, requirements.txt, and all source code

## 12.2 Competition-Specific Acceptance Criteria

| Deliverable | Format | Criteria | Due Date |
| --- | --- | --- | --- |
| Research Poster | 30×40 landscape, printed | All 8 figures present, references listed, QR code to demo | Week 6 (Mar 23) |
| Academic Presentation | 12 min, slides + live demo | Timed to 12 min ±30 sec; demo shows 2+ tabs | Week 7 (Apr 3) |
| Industry Pitch | 2 min, no slides | Market sizing, competitive landscape, monetization | Week 7 (Apr 3) |
| Midpoint Video | 60–120 sec, uploaded | Shows problem + preliminary AF3 output | Week 6 (Mar 20) |

# 13. DEPENDENCIES & EXTERNAL SERVICES

| Service | URL | Account Required | Rate Limits | Criticality |
| --- | --- | --- | --- | --- |
| AlphaFold Server | alphafoldserver.com | Google account | ~20 jobs/day, 5000 tokens/job | Critical (Module 1) |
| RCSB PDB | rcsb.org | No | None | Critical (Module 1) |
| UniProt | uniprot.org | No | None | Critical (Module 1) |
| PubChem | pubchem.ncbi.nlm.nih.gov | No | 5 req/sec (API) | Critical (Module 2) |
| SwissADME | swissadme.ch | No | None (manual) | Important (Module 2) |
| GPCRdb | gpcrdb.org | No | None | Optional (context) |
| AlphaFold DB | alphafold.ebi.ac.uk | No | None | Backup (pre-computed WT structures) |

# 14. APPENDIX: FILE NAMING CONVENTIONS

## 14.1 Structure Files

| Pattern | Example | Description |
| --- | --- | --- |
| pred_{receptor}_{ligand}.cif | pred_hM4Di_DCZ.cif | AF3 predicted structure |
| pred_{receptor}_apo.cif | pred_hM4Di_apo.cif | AF3 predicted structure without ligand |
| exp_{pdb_code}.pdb | exp_7WC6.pdb | Experimental cryo-EM structure |
| plddt_{receptor}_{ligand}.json | plddt_hM4Di_DCZ.json | pLDDT confidence scores |

## 14.2 Figure Files

| Pattern | Example | Description |
| --- | --- | --- |
| fig_rmsd_bar.png | fig_rmsd_bar.png | RMSD comparison bar chart |
| fig_plddt_{receptor}.png | fig_plddt_hM4Di.png | pLDDT per-residue confidence plot |
| fig_overlay_{receptor}.png | fig_overlay_hM4Di.png | Predicted vs experimental structure overlay |
| fig_chemical_space.png | fig_chemical_space.png | LogP vs TPSA scatter with BBB zones |
| fig_radar_{compound}.png | fig_radar_DCZ.png | Property radar chart for a compound |
| fig_boiled_egg.png | fig_boiled_egg.png | SwissADME BOILED-Egg BBB plot |

## 14.3 Version Control

- Use Git for version control; push to GitHub at least daily during development weeks

- Branch strategy: main (stable), dev (active work), feature/* (per-module)

- Commit messages: conventional format (feat: ..., fix: ..., docs: ...)

- Tag releases: v0.1.0 (Module 1 done), v0.2.0 (Module 2 done), v0.3.0 (Dashboard done), v1.0.0 (competition-ready)

END OF DOCUMENT

PRD Version 1.0 • February 25, 2026